## Sheet1
TIMESTAMP | UAT USER | USER TYPE | STATUS | CRITICALITY | TEST CASE ID | PRIMARY CATEGORIZATION | SECONDARY CATEGORIZATION | TEST CASE DESCRIPTION | DESCRIPTION | COMMENTS | UAT PHASE
2025-02-14 12:00 | Amber | Super | Closed | Medium | P1-TC-D-04 | Calculation Error | Incorrect TDP calculation values | Validation of calculation of TDP related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | CKNUTTERBUTTERFS - the TDPs show up as 0 when the # is really 113 - we can't divide by 1000 on this row |  | 1
2025-02-12 14:23 | Manoel | Super | In Progress | Medium | P1-TC-D-05 | Calculation Error | Incremental LBS mismatch in SWA | Validation of calculation of Incremental related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Example of CRGRAHAMS month of Feb 24 shows Incremental LBS that are 10.7% lower in SWA than in the NIQ data; SEE EXAMPLES TAB |  | 1
2025-02-12 14:23 | Manoel | Super | Opened | High | P1-TC-D-06 | Calculation Error | Incorrect YoY Trend Calculation | Validation of calculation of Category Base Trend related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Example of CRGRAHAMS: YoY Base Category Trend % matches input file, but "YoY Base Category Trend Base LBS / TDP" do no show the expected result. See EXAMPLES tab. |  | 1
2025-02-12 14:23 | Manoel | Super | Opened | High | P1-TC-D-07 | Mapping Alignment | Missing data in Innovation table | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Example of FAIL: CRRITZREG had an innovation SKU launch in Oct-24 (NIM Consolidation file, All Brands Seasonal tab) but the volume is not appearing in the SWA Innovation table. Same is happening for CKHANDISNACKS that has innovation starting in Feb-24. Details on EXAMPLES tab. Example of PASS: CLIF 6PK Innovation SKU is pulling in starting Nov-24 and data matches Nielsen data exactly! :) |  | 1
2025-02-13 15:00 | Manoel | Super | In Progress | High | P1-TC-D-10 | Mapping Alignment | Variance in LBS calculation | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CLIF BAR 6 PACK has variances of 20% in the LBS compared to Nielsen. Likely due to some UPCs having a different units to lbs conversion than others in the same IBP Subfamily due to PPA change. Also noting that the GR$ is off slightly, and the gap seems to be made up of two UPCs that should be mapping but maybe are falling off for some unknown reason |  | 1
2025-02-12 14:23 | Manoel | Super | Closed | High | P1-TC-D-11 | Calculation Error | Incorrect Baseline Calculation | Validate if the Actual brand baseline calculation is accurate for a preset IBP Category, Brand, DP Owner, and SF. | Brand Baseline is not calculating the difference of CORE Base Velocity YoY and may be looking at total Base Velocity less other drivers - this is apparent in the Clif file months Oct-Dec '24 |  | 1
2025-02-13 15:00 | Manoel | Super | In Progress | High | P1-TC-D-18 | Calculation Error | Enrichment impact on calculations | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | For CLIF BAR 6 PACK, tested putting Enrichment in April '25 of +2000. It looks like more than just the month of April '25 changes in other tables after the enrichment is entered but it does not flow through to the Actuals + Forecast tab or the data export. When I refresh SWA, the Enrichment is wiped out. |  | 1
2025-02-13 15:00 | Manoel | Super | In Progress | Medium | P1-TC-D-33 | Visualization Issue | Missing Graphs for Section | Check the Forecast charts for each of the previous test cases. | CKBELVITA is not showing Brand Baseline Base LBS/TDP in the "components" graph |  | 1
2025-02-17 12:00 | Manoel | Super | In Progress | High | P1-TC-D-37 | Mapping Alignment | Unmapped and Incorrectly Mapped UPCs | Validate if the brand-category level volume matches the expected values or not for both Actuals and forecast window. | The total $ values do not match the Nielsen report; There are a few things that seem to be happening - there are unmapped Nielsen UPCs that wont tie to the brand, and there also seem to be UPCs that are mapped that aren't pulling into SWA. See Luna 6pk example P1-TC-D-10 |  | 1
2025-02-17 12:00 | Manoel | Super | Opened | Medium | P1-TC-D-39 | Mapping Alignment | Table volume validation issues | Validate if all the table shows volume for both Actuals and forecast window for each driver. | Incremental is missing to add - table should start with PY Total Consumption LBS and build to CY Total Consumption LBS |  | 1
2025-02-12 14:23 | Manoel | Super | In Progress | Medium | P1-TC-F-06 | Calculation Error | Multiple IBPSFs not summed | It is easy to set up the slicers to get the data I need | Failed due to issues in prior scripts. Also, I would expect if you select multple IBPSFs, you would see the values added together. I don't think there is much benefit to being able to select multiple IBPSFs if the data is still separate. |  | 1
2025-02-12 14:23 | Manoel | Super | Closed | High | P1-TC-F-07 | Calculation Error | Division by zero issue | The tables are clear and easy to navigate | Marking this as fail only due to request above to change TDPs so that they are not divided by zero. Also would recommend showing percentages with only one decimal point |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-02 | Mapping Alignment | Incorrect subfamily pack size data | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Data for subfamilies that transitioned to new pack sizes is incorrect. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-03 | Mapping Alignment | Incorrect subfamily data mapping | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Data for subfamilies that transitioned to new pack sizes is incorrect. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-04 | Mapping Alignment | Incorrect data for new pack sizes | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Data for subfamilies that transitioned to new pack sizes is incorrect. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-05 | Mapping Alignment | Incorrect data for transitioning subfamilies | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Data for subfamilies that transitioned to new pack sizes is incorrect. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-06 | Calculation Error | Incorrect TDPs values causing zeros | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | TDPs are all zeros. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-07 | Mapping Alignment | Mapping Alignment | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Data for subfamilies that transitioned to new pack sizes is incorrect. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-08 | Calculation Error | Discrepancy in pound calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | There's nothing but Oreo on the input file. When I compare against my current model the calendar stuff looks right but the lbs are off for all packs. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-09 | Visualization Issue | Table-Graph Data Mismatch | Check the Actual charts for each of the previous test cases. | Total CX MBD Drivers PY Total Lbs match but CY Total Lbs is on the chart but not on the table. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-13 | Calculation Error | Negative forecast values post-2026 | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Lbs are way below LY and are negative starting in 2026. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-14 | Calculation Error | Negative Forecast from 2026 | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Lbs are way below LY and are negative starting in 2026. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-15 | Calculation Error | Forecast metrics display zero values | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Almost every metric is zeros. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-16 | Calculation Error | Forecast Values All Zero | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | TDPs are zeros. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-17 | Calculation Error | Zero incremental dollars issue | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Incremental $ are zeros when Lbs are >0. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-18 | Mapping Alignment | Missing validation reference data | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | There's nothing but Oreo in the Untracked input file so I don't know what to validate against. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-25 | Calculation Error | Missing consumption data for Clif Bar | Validate if all the table shows volume for both Actuals and forecast window for each driver. | Total Consumption $ not populating for Clif Bar. |  | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | Medium | P1-TC-D-26 | Mapping Alignment | Drill down Clif Bar Volume | Validate if user is able to drill down to Brand level/Category/Sub Family level and visualize all drivers volumes for actual window. Note: Forecast window based on Cx% provided by planners's build is in Progress and will be ready in Phase 2. | Total Consumption $ not populating for Clif Bar. |  | 1
2025-02-12 14:23 | Richard | Normal | Closed | Medium | P1-TC-D-22 | Visualization Issue | Gap in chart display | Check the Actuals + Forecast charts for each of the previous test cases. | there is a gap in the graph between Act and Forecast |  | 1
2025-02-12 14:23 | Richard | Normal | Closed | High | P1-TC-F-02 | Mapping Alignment | Incorrect filter setup | Set up the Consumption view for one or more IBP Subfamilies | there are brands in the 'demand planner owner' filter |  | 1
2025-02-12 14:23 | Richard | Normal | Closed | Medium | P1-TC-R-02 | Mapping Alignment | Incorrect Retail Data Filtering | Adjust Summary IBP Category Breakdown to Retail data only and verify data quality. | I can see the total but not filter anything by Retail , just by IBP brand |  | 1
2025-02-12 14:23 | Richard | Normal | Closed | High | P1-TC-R-03 | Mapping Alignment | Filter option for MUPS only | Adjust Summary IBP Category Breakdown to MUPS data only and verify data quality. | I can see the total but not filter anything by MUPS , just by IBP brand |  | 1
2025-02-12 14:23 | Richard | Normal | Closed | Medium | P1-TC-R-04 | Format Modification | Filtering by Channels issue | Adjust Summary IBP Category Breakdown to Channels data only and verify data quality. | I can see the total but not filter anything by Channels , just by IBP brand |  | 1
2025-02-12 14:23 | Richard | Normal | Closed | High | P1-TC-R-05 | Mapping Alignment | Improper category data filtering | Adjust Summary IBP Category Breakdown to Food Service data only and verify data quality. | I can see the total but not filter anything by Foodservice , just by IBP brand |  | 1
2025-02-12 14:23 | Richard | Normal | Closed | Medium | P1-TC-R-11 | Visualization Issue | Table-Graph Data Mismatch | Create a waterfall chart with the full dataset or part of it. | the waterfall for Brand trends looks wrong, the export adds to $221 and the Graph is $84M - all the other drivers match |  | 1
2025-02-12 14:23 | Kelly | Super | Closed | High | P1-TC-D-01 | Calculation Error | Negative trend despite positive data | Validate if the Actual brand baseline calculation is accurate for a preset IBP Category, Brand, DP Owner, and SF. | I get a negative brand trend base lbs/TDP (month) in sep/oct, but both base lbs and TDPs are positive. Specifically looked at sep/oct 2024 for CKOREOFS |  | 1
2025-02-12 14:23 | Kelly | Super | Closed | Medium | P1-TC-D-17 | Format Modification | Data format hinders validation | Validate if the forecast trends looks reasonable based on actuals data for a preset IBP Category, Brand, DP Owner, and SF. | its hard to tell because of the formatting but I feel like this is missing data. (Pic on defect log) |  | 1
2025-02-12 14:23 | Kelly | Super | Closed | Medium | P1-TC-D-33 | Visualization Issue | Forecast Charts Error Message | Check the Forecast charts for each of the previous test cases. | error message (pic on defect log) |  | 1
2025-02-12 14:23 | Manoel | Super | Closed | High | P1-TC-D-01 | Calculation Error | Brand baseline calculation accuracy | Validate if the Actual brand baseline calculation is accurate for a preset IBP Category, Brand, DP Owner, and SF. | Brand Baseline is not removing the impact from PPA. See EXAMPLES tab. It is correctly removing Category Base Trend and Pricing |  | 1
2025-02-14 12:00 | Manoel | Super | Closed | Medium | P1-TC-D-02 | Calculation Error | Missing PPA inputs in SWA | Validation of calculation of PPA related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Looking for PPA inputs for CKOREOTHINSFS that started in March 2024 per the PPA input file but not seeing any inputs in SWA |  | 1
2025-02-13 15:00 | Manoel | Super | Opened | High | P1-TC-D-03 | Calculation Error | Incorrect pricing action timeframe | Validation of calculation of Pricing Action related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Time horizon is too large. Should only see impact for first 12 months of pricing action; this would align with the months indicated on the input file. See EXAMPLES tab |  | 1
2025-02-13 15:00 | Manoel | Super | Closed | High | P1-TC-D-34 | Calculation Error | Forecast missing for CRGRAHAMS | Validate if the forecast is available for next 24 months for total forecast for a preset IBP Category, Brand, DP Owner, and SF. | Forecast is missing for CRGRAHAMS in all tables execept Incremental |  | 1
2025-02-17 12:00 | Manoel | Super | Closed | Medium | P1-TC-D-41 | Visualization Issue | Waterfall Tooltip Wrong Values | Validate if waterfall represent the volume correctly or not. | Values match Demand Drivers, yay! Only weird thing I see is when I hover over the MBD blocks different values appear. For example, GRGRAHAMS for 2024-all shows -15K LBS for Brand Trend but the hover over label shows 49K. |  | 1
2025-02-19 12:00 | Kelly | Super | In Progress | High | P2-TS-D-03 | Calculation Error | Incorrect category total CY Lbs | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CY Total CX Lbs are wrong (CKOREOINANDOUT). Example- Jan 24 I have 88k, SWA has 24k |  | 2
2025-02-19 12:00 | Kelly | Super | Opened | High | P2-TS-D-04 | Calculation Error | Incorrect values for sub families | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CKOREOFS: I see all 2s. Looked wrong for other sub families too |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | High | P2-TS-D-06 | Calculation Error | Incorrect Actual Build/Burn Calculation | Validation of calculation of Actual Build/Burn related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | really high.. Would expect to see between -2MM and +2MM on CKOREOFS |  | 2
2025-02-19 12:00 | Kelly | Super | Opened | Medium | P2-TS-D-08 | Mapping Alignment | Mismatch with model input | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CKOREOFS: doesn’t match my model gregorian impact |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | High | P2-TS-D-09 | Calculation Error | Incorrect monthly pounds calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CKOREOFS: would expect to see closer to 2MM lbs in a month, not 23MM |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | High | P2-TS-D-10 | Mapping Alignment | Actuals values double expected | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CKOREOFS: way too high. Expect to see more like 20MM lbs in a month. This is double. Checked multiple sub families too. All about double |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | Medium | P2-TS-D-11 | Calculation Error | Data mismatch with offline model | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Data doesn’t match my offline model (CKOREOFS) |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | Critical | P2-TS-D-15 | Calculation Error | Negative Cx forecast issue | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | CKOREOINANDOUT negative Cx forecast in some months |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | High | P2-TS-D-16 | Calculation Error | Forecast presents incorrect data | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | CKOREOTHINSFS ALL 2's. Not right |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | Low | P2-TS-D-17 | Format Modification | Add unit to input | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | I think this works but can we add a unit or something. I am not sure what entering "2" means or does to the forecast |  | 2
2025-02-19 12:00 | Kelly | Super | Closed | High | P2-TS-D-18 | Calculation Error | Forecasted Build calculation issue | Validation of calculation of Forecasted Build/Burn related drivers for forecast timeframe for a preset IBP Category, Brand, DP Owner, and SF. | same as build/burn actuals:Too high |  | 2
2025-02-24 12:00 | Kelly | Super | Opened | High | P2-TS-D-30 | Calculation Error | Incorrect actuals value calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | way too high (lbs is closer to GR.. Lbs should be closer to 18k per month, and GR close to 80k per month) |  | 2
2025-02-24 12:00 | Kelly | Super | Closed | High | P2-TS-D-31 | Calculation Error | Actuals Calculation Too High | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | way too high |  | 2
2025-02-24 12:00 | Kelly | Super | Closed | High | P2-TS-D-32 | Calculation Error | Forecast numbers too high | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | way too high (lbs is closer to GR.. Lbs should be closer to 18k per month, and GR close to 80k per month) |  | 2
2025-02-24 12:00 | Kelly | Super | Closed | High | P2-TS-D-33 | Calculation Error | Forecast values are too high | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | way too high |  | 2
2025-02-20 12:00 | Amber | Super | Closed | Medium | P2-TS-D-24 | Visualization Issue | Incorrect chart line positioning | Check the Forecast charts for each of the previous test cases. | In Cx to Tracked Shipment Chart, the "CY Total Lbs" line is on the bottom. I expected that to be top line - it's Total, shouldn't it be? |  | 2
2025-02-19 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-03 | Calculation Error | Mismatched CY Total CX Lbs | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Fail for CRGRAHAMS - the "CY Total CX Lbs" should match LBs in the Total IBP Sub Family table |  | 2
2025-02-19 12:00 | Manoel | Super | Closed | Medium | P2-TS-D-12 | Visualization Issue | Chart label needs correction | Check the Actual charts for each of the previous test cases. | Tracked Shipment Adjustments chart for "comparison" should say "CY Total CX Lbs" instead of CY Total Lbs |  | 2
2025-02-19 12:00 | Manoel | Super | Closed | Medium | P2-TS-D-25 | Mapping Alignment | Tables and views consistency | Check if the combined tables match the individual views. | Build/burn enrichment doesn't show up on the Actuals + Forecast tab |  | 2
2025-02-19 12:00 | David | Super | Closed | Critical | P2-TS-D-07 | Calculation Error | Liquidations misaligned with input file | Validation of calculation of Liquidations and Returns for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Liquidations not aligned to input file when I filter on OREOTHINs subfamilies |  | 2
2025-02-21 12:00 | Manoel | Super | Closed | Medium | P2-TS-D-24 | Visualization Issue | Incorrect Chart Label Display | Check the Forecast charts for each of the previous test cases. | Defect logged for Actuals but also a defect for the Forecast: Tracked Shipment Adjustments chart for "comparison" should say "CY Total CX Lbs" instead of CY Total Lbs |  | 2
2025-03-13 12:00 | Kelly | Super | Closed | Low | P3-EE-D-03 | Calculation Error | Erratic shipment volume forecast | Check the Forecast values in order of magnitude for all the drivers. | shipment volume gets really crazy in sep 25 for CKOREOFS |  | 3
2025-03-13 12:00 | Kelly | Super | Closed | Medium | P3-EE-D-05 | Calculation Error | Incorrect PPD calculation in forecast | Validate if PPD is captured properly and removed from Total Forecast. | looks to be doubled for some sub families. CKOREOFSINANDOUT should be 203k ppds for April, 222k for May, etc |  | 3
2025-03-13 12:00 | Kelly | Super | Closed | Medium | P3-EE-D-06 | Calculation Error | NIAPO Calculation and Mapping Issues | Validate if NIAPO Calculation is reflecting properly and Total Forecast is adjusted appropriately. | everything should be in APO for 2025 CKOREOFSINANDOUT… could be that the data is old though? Cant find the mapping for NIAPO items though |  | 3
2025-03-13 12:00 | Kelly | Super | Closed | Critical | P3-EE-D-08 | Calculation Error | Incorrect Actuals in Charts | Check the Actual+Forecast charts for all the drivers. | actuals section in screenshot is wrong. Looking at CKOREOPARTYPACK, but checked multiple. Example, december 2024 should be 17.6MM, not 34MM. Nov should be 14.2MM, not 33.7MM |  | 3
2025-03-13 12:00 | Kelly | Super | Opened | Critical | P3-EE-D-09 | Calculation Error | Drilldown drivers volume discrepancy | Validate if user is able to drill down to Brand level/Category/Sub Family level and visualize all drivers volumes for actual & forecast window. Note: Actual window leverages Nielsen Cx actual ratio while forecast uses Cx% provided as manual input for SF-Brand Disagg. | got an error |  | 3
2025-03-13 12:00 | Kelly | Super | In Progress | High | P3-EE-D-11 | Calculation Error | Incorrect percentage calculation | Validate the calculation of Category-Brand level total ship adjustments to ensure SF-Brand Disagg is carried out appropriately. | tested CLUBMUPS to Oreo. Should get 51% and it was much less than that |  | 3
2025-03-13 12:00 | Manoel | Super | Closed | Medium | P3-EE-D-03-1 | Calculation Error | Forecast values mismatch with untracked file | Check the Forecast values in order of magnitude for all the drivers. | Forecast: Forecast for GRECOMM (ALL and TRISCUIT, for example) does not match the Untracked Input file |  | 3
2025-03-13 12:00 | Manoel | Super | Closed | Medium | P3-EE-D-03-2 | Calculation Error | Missing forecast values in table | Check the Forecast values in order of magnitude for all the drivers. | Forecast: CLUBMUPS without any other filters shows no values for Mar 25 - Dec 25 on the Total IBP Forecast (NIQ Facts) table despite there being a forecast in the Total CX MBD Drivers section |  | 3
2025-03-13 12:00 | Manoel | Super | Closed | Critical | P3-EE-D-06 | Calculation Error | Incorrect NIAPO Calculation Mapping | Validate if NIAPO Calculation is reflecting properly and Total Forecast is adjusted appropriately. | CKCHIPSAHOYFS has Provisional SKUs (NIAPO) on the NIM Consolidation file, however, there is no forecast in Column AE which is the one that is supposed to feed SWA for the NIAPO Removal; SWA is showing values in NIAPO which means it must be pulling from an incorrect column |  | 3
2025-03-13 12:00 | Manoel | Super | Closed | Medium | P3-EE-D-07-2 | Calculation Error | Missing Untracked Forecast Values | Check the Actual+Forecast values in order of magnitude for all the drivers. | Actuals & Forecast: For CLUBCR04782TRIS, I am unable to see the Untracked forecast for the entire time horizon; it looks like this is due to the CX Actuals being 0 for certain months, but I would still expect to see those months in the tables and the Untracked input for that month as well |  | 3
2025-03-17 12:00 | Manoel | Super | Opened | Medium | P3-EE-D-08 | Visualization Issue | Charts not showing future months | Check the Actual+Forecast charts for all the drivers. | Total CX MBD Drivers Charts horizon is only for actual months - need to show this for future months |  | 3
2025-03-14 12:00 | Manoel | Super | Closed | Medium | P3-EE-F-07-1 | Format Modification | Freeze top row in table | The tables are clear and easy to navigate | For long tables, like Total CX MBD Drivers and Core Base Velocity, can we please freeze the top row with the month so that it can still be seen when you are looking at the bottom of the table? This is especially important for Brand Baseline, as planners will need to be able to see the month that they are entering enrichments against. If freezing can't be done I'd recommend moving Brand Basele to the first section (before Pricing). Also could make the Total CX MBD Drivers table shorter by splitting the YoY % section to it's own table |  | 3
2025-03-14 12:00 | Manoel | Super | Closed | Medium | P3-EE-F-07-2 | Visualization Issue | Month headers misalignment with values | The tables are clear and easy to navigate | When I scroll right across tables, the month headers don't align with the numberical values |  | 3
2025-03-14 12:00 | Manoel | Super | Closed | Critical | P3-EE-F-07-3 | Format Modification | Table layout revision requested | The tables are clear and easy to navigate | We need a table that has "CY Tracked Shipment LBS", "Untracked Shipment Lbs", "Liquidations" and "Shipment Volume (LBS)" all in one - discussed with Hektor adding these 3 rows to the "Total Shipment - Lbs & GR$" table; would also like a chart to graph these 3 elements |  | 3
2025-03-14 12:00 | Manoel | Super | Closed | High | P3-EE-F-08 | Visualization Issue | Incorrect data labels on graph | The graphs provided are easy to read | The graph for Gregorian Adjustment of Consumption should graph "CY Total CX Lbs" and "CY Tracked Shipment Lbs" and not "CY Tracked Shipment Total" |  | 3
2025-03-14 12:00 | Matheus | Normal | Closed | High | P3-EE-D-07 | Visualization Issue | Drill down visualization error | Validate if user is able to drill down to Brand level/Category/Sub Family level and visualize all drivers volumes for actual & forecast window. | I get an error message |  | 3
2025-02-14 12:00 | Sonny | Super | In Progress | Medium | P1-TC-D-04 | Calculation Error | Mismatched Data for TDP Calculation | Validation of calculation of TDP related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | CKOREO tested. Checked Total TDP in the Input File from Oct-24 to Dec-24. Data didn't match | Data didn't match | 1
2025-02-14 12:00 | Theodore | Normal | Opened | Low | P1-TC-D-20 | Calculation Error | Incorrect forecast data availability | Validate if the forecast is available for next 24 months for total forecast for a preset IBP Category, Brand, DP Owner, and SF. | Validating MBD forecast for 24 months | Some drivers do not have data until 2026 and PY numbers are not feeding in 2026 (e.g. PY Incremental LBs) | 1
2025-02-14 12:00 | Theodore | Normal | Opened | Medium | P1-TC-D-21 | Mapping Alignment | Data flow inconsistency detection | Check if the combined tables match the individual views. | Validating CY Total Cx lbs for Actuals + Fcst flowing through properly with baseline enrichment | Enrichment impact can be seen in CY Total Cx Lbs Fcst, but not flowing through in the CY Total Cx Lbs Actuals + Fcst for the same time period | 1
2025-02-13 15:00 | Theodore | Normal | Opened | Medium | P1-TC-R-06 | Format Modification | Filters resetting with changes | Adjust the Absolute Volume table and verify data quality. | Trying to switch years in filter for data | All other filters reset when the year filter is changed | 1
2025-02-13 15:00 | Theodore | Normal | Opened | Medium | P1-TC-R-07 | Calculation Error | Table data not updating | Adjust the Absolute Volume table and verify data quality. | Trying to filter monthly data in Summary Visuals | Data in table not updating according to the month filter | 1
2025-02-13 15:00 | Manoel | Super | In Progress | Medium | P1-TC-D-16 | Visualization Issue | PY-CY Data Mismatch | Check the Actual charts for each of the previous test cases. | "Incr Lbs" chart is graphing PY values as current year values | Example is Clif Bar 6 Pack | 1
2025-02-13 15:00 | Manoel | Super | In Progress | Medium | P1-TC-D-17 | Visualization Issue | Missing Graphs for Section | Check the Actual charts for each of the previous test cases. | "Impact" chart is missing YoY Incremental | Example is Clif Bar 6 Pack | 1
2025-02-14 12:00 | Manoel | Super | Opened | Low | P1-TC-D-35 | Format Modification | Inconsistent table formatting comparison | Check if the combined tables match the individual views. | Formatting of the Core Base Velocity table looks different between historical months vs future months | Example is CKBELVITA | 1
2025-02-17 12:00 | Manoel | Super | In Progress | High | P1-TC-D-38 | Mapping Alignment | UPCs mapping discrepancy identified | Validate if the brand-category level volume matches the expected values or not for both Actuals and forecast window. | Logging similar issue to P1-TC-D-10 for Luna 6 PACK; this one impacting Nutter Butter total CX$ value on the Summary IBP Brand table. Gap for Jan '24 is $606,985 for mapped UPCs. This gap is made up of UPCs with SKU status 6 and 4. | See NUTTER BUTTER tab | 1
2025-02-17 12:00 | Manoel | Super | Opened | High | P1-TC-D-40 | Mapping Alignment | Drill down visualization mismatch | Validate if user is able to drill down to Brand level/Category/Sub Family level and visualize all drivers volumes for actual window. Note: Forecast window based on Cx% provided by planners's build is in Progress and will be ready in Phase 2. | Brand Baseline (Brand Trend) does not match what is on Demand Drivers (CRGRAHAMS example); Incremental is missing to add - table should start with PY Total Consumption LBS and build to CY Total Consumption LBS | See "Total Drivers" tab | 1
2025-02-17 12:00 | Manoel | Super | In Progress | Medium | P1-TC-R-04 | Mapping Alignment | Missing data for CLUBCR02923WTSC | Adjust Summary IBP Category Breakdown to your brand and evaluate the data quality for the Channels line only. | Noticing missing categories like Channels where there should be values - example is Wheat Thins that should have Club volume. Looks like IBP Subfamily CLUBCR02923WTSC is not pulling in any consumption data on the Drivers table and is therefore missing from the Summary. | CLUBCR02923WTSC maps to Nielsen UPC 4400000962 which has CX volume in Nielsen report but is not pulling into SWA | 1
2025-02-13 15:00 | Jose | Normal | In Progress | Low | P1-TC-R-02 | Mapping Alignment | Filter Options for Retail Line | Adjust Summary IBP Category Breakdown to your brand and evaluate the data quality for the Retail line only. | not an option to adjust to Retail only , the information does not change | the only filter available is IBP Brand | 1
2025-02-14 12:00 | Matheus | Normal | In Progress | High | P1-TC-D-03 | Calculation Error | Incorrect total calculation expected | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp. I would have assumed the total ibp sub famil (niq facts) would be the sum of the core and innovation tables. Ex dec '24 base lbs for core is 709, innovation lbs is 220. so I would have thought it would show 929 in lbs on the total ibp sub famil (niq facts) tables. right now core matches exactly to total ibp sub famil (niq facts). | I expect the total ibp sub famil (niq facts) to be the sum of core and innovation table. | 1
2025-02-14 12:00 | Matheus | Normal | Opened | Low | P1-TC-D-18 | Calculation Error | Missing forecast data for 2026 | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | no 2026 data | should have data | 1
2025-02-12 14:23 | Matheus | Normal | Opened | Medium | P1-TC-F-01 | Mapping Alignment | Brand and subfamily consistency | The user should be able to set IBP Category, Brand, and one or more IBP Subfamilies and see updated tables with data. | It would be great if when you select an IBP subfamily the IBP Brand selection removes the Brands that arent in that sub family. For example, I select GRVARIETYPACK. All the brands are still list but I click on belvita and nothing populates and it resets my selection. its becasue belvita isnt includes in the that subfamliy. | Instead of guessing what brands are in my ibp subfamily. It would be nice if the ibp brand removes the brands that aren't in the ibp subfamily. EX. I select grvarietypack and then my brand options should only be oreo, ca!, nutterbutter, nilla, teddy, all other cookie, barnums, ritz). | 1
2025-02-12 14:23 | Matheus | Normal | Opened | Medium | P1-TC-F-02 | Mapping Alignment | Incorrect total line generation | The user should be able to set IBP Category, Brand, and one or more IBP Subfamilies and see updated tables with data. | When I select an IBP category (MUPS) and an IBP Subfamily (GRVARIETYPACK), I get multiple "total" lines which I believe is for each brand represented in the ibp subfamily (even though that is also incorrect since there are 8 brands in this subfamily). EX. I have 4 "PY Total LBS" lines. In MUPs, we don’t speak at the ibp subfam & brand level. we speak in ibp subfam level. In mups we speak in ibp sub family and dont care what brands are included. if we have to filter by brand+ibpsubfam, i will have to review 50+ cx forecast each month. | I expect to have one total line for each key figure when selecting an IBP subfamily no matter how many brand fall under that subfamily. | 1
2025-02-12 14:23 | Matheus | Normal | In Progress | Low | P1-TC-F-03 | Mapping Alignment | Missing actuals for specific brands | The user should be able to set IBP Category, Brand, and one or more IBP Subfamilies and see updated tables with data. | Teddy brand isnt populating actuals in the grvarietypack subfam when it should. Skus 440000783900 & 440000409800 | I expect actuals to populate. This isnt the only brand missing information in actuals for grvariteypack. | 1
2025-02-13 15:00 | Matheus | Normal | Opened | Low | P1-TC-F-04 | Mapping Alignment | Incorrect options for selection | Set up the Consumption view for IBP Category, Brand, DP Owner, and IBP Subfamily | This may fall under the master data side, if so ignore, but when selecting Demand Planner Owner MOSER GR the only IBP Category to come up should be MUPs. | Only my ib categories, brands and sub familes should come up as optins when selecting my dp ower code | 1
2025-02-14 12:00 | Matheus | Normal | Opened | Medium | P1-TC-R-07 | Calculation Error | Missing Actuals Data | Adjust the Absolute Volume table and verify data quality. | I don't have actuals for distribution or innovation | should have data | 1
2025-02-14 12:00 | David | Super | Opened | High | P1-TC-D-01 | Calculation Error | Discrepancies in monthly totals | As a user, I can login into the Shiny Web App (SWA) by providing credentials (LAN ID and MDLZ Password). | Validate if the Actual brand baseline calculation is accurate for a preset IBP Category, Brand, DP Owner, and SF. | I pulled all subfamilies that fell under OREO and compared the rolled up totals to our Cx actuals for NAB OREO. There is fairly significant discrepancies every month. | 1
2025-02-14 12:00 | David | Super | Opened | High | P1-TC-D-02 | Calculation Error | Incorrect data timeframe in calculations | Set up the Consumption view for one or more IBP Subfamilies | Validation of calculation of PPA related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | I saw values in CKOREOPARTYPACK where I was expecting to see PPA numbers - but the data should have only started in march, but I see it in Jan/Feb. | 1
2025-02-14 12:00 | David | Super | Opened | High | P1-TC-D-03 | Calculation Error | Incorrect data timeframe displayed | Set up the Consumption view for IBP Category, Brand, and IBP Subfamily | Validation of calculation of Pricing Action related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | I saw values in CKOREOFS where I was expecting to see numbers - but the data should have only started in march, but I see it in Jan/Feb | 1
2025-02-14 12:00 | David | Super | Opened | Medium | P1-TC-D-04 | Calculation Error | Formula outdated causing mismatch | Set up the Consumption view for IBP Category, Brand, DP Owner, and IBP Subfamily | Validation of calculation of TDP related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | I saw values in CKOREOpartypack where I was expecting to see numbers - but the data stopped matching after september. The formulas in the input file were not up to date so I'm assuming that was the issue there. | 1
2025-02-14 12:00 | David | Super | In Progress | High | P1-TC-D-11 | Calculation Error | Incorrect total Cx calculation | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Numbers match an Excel validator/calculation by hand/system check. | I pulled CKOREOFS from SWA UAT NIQ REPORTS and the total Cx is off so Core is also off | 1
2025-02-14 12:00 | David | Super | Opened | High | P1-TC-D-17 | Calculation Error | Increasing trends discrepancy issue | Validate if the forecast trends looks reasonable based on actuals data for a preset IBP Category, Brand, DP Owner, and SF. | Forecast to look reasonably close to actuals - graphical validation can be performed as well to check trends. | The Base lbs per TDP were increasing 6-9% per month after May which feels way too high, but it's possible that the input was just too high | 1
2025-02-14 12:00 | David | Super | Opened | High | P1-TC-D-19 | Calculation Error | Duplication and missing key figures | Validation of calculation of PPA related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Numbers should match the Input file for all attributes coming from Input Data, all other calculations to be validated by hand/system/excel | The only subfamily that has PPA next year is GRVARIETYPACK and maybe some of the other VP subfamilies. The rows are duplicative and do not include all the key figures needed for this subfamily | 1
2025-02-14 12:00 | David | Super | In Progress | High | P1-TC-D-26 | Calculation Error | Discrepancies in rolled-up totals | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Numbers match an Excel validator/calculation by hand/system check. | Rolled up Total Cx amonst all OREO Retail PPGs and had some volume discrepancies worth about 1.5% on the year. There are no Cx $s comging into the model though | 1
2025-02-14 12:00 | David | Super | Opened | High | P1-TC-D-27 | Calculation Error | CKOREOParty mismatch specific months | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Numbers match an Excel validator/calculation by hand/system check. | CKOREOParty is not matching the latest rack up especially in specific months | 1
2025-02-14 12:00 | David | Super | In Progress | Medium | P1-TC-D-37 | Calculation Error | Volume mismatch in forecast | Validate if the brand-category level volume matches the expected values or not for both Actuals and forecast window. | Brand-category level volume should match as per Nielsen Brand-SF actual % disagg ratio while for forecast it will follow Cx % calculation. | Total Oreo Cx does not match actuals in Nielsen for Total Oreo | 1
2025-02-17 12:00 | Jonathan | Normal | In Progress | High | P1-TC-D-12 | Calculation Error | Pricing and PPA elasticity issue | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Base trend math doesn't check out. NIQ lbs are very understated (tested Clif Singles). Pricing elasticity doesn't seem to be feeding through. PPA elasticity doesn't seem to be feeding through (6pks). | Retest: NIQ data (Lbs, Base Lbs) does not match Prior Year numbers for Clif Singles. | 1
2025-02-13 15:00 | Manoel | Super | Opened | High | P1-TC-D-09 | Calculation Error | Incorrect YoY distribution calculation | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | YoY Distribution calculation isn't working properly - it should take YoY Change in CORE TDPs and multiply by the Current Year CORE Base LBS/TDP. Missing the YoY New Item Velocity and YoY New Item TDP split - can we discuss adding this to the innovation table instead of the total Drivers table? | See row 15 of the "Total Drivers" tab of the linked file for the correct formula | 1
2025-02-14 12:00 | Matheus | Normal | Opened | High | P1-TC-D-08 | Calculation Error | Shipment lbs total mismatch | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp | I assume this should be the total of untracked and track shipment lbs. | 1
2025-02-14 12:00 | David | Super | Opened | High | P1-TC-D-20 | Calculation Error | Pricing data mismatch February | Validation of calculation of Pricing Action related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Numbers should match the Input file for all attributes coming from Input Data, all other calculations to be validated by hand/system/excel | There should have been pricing for CKOREOFS in Feb 25 but there are all 0s | 1
2025-02-14 12:00 | David | Super | In Progress | High | P1-TC-D-41 | Visualization Issue | Waterfall volume calculation discrepancy | Validate if waterfall represent the volume correctly or not. | Waterfall should represent the right volumes as per the backend data and calculation must match the appropriate aggregation rules. | Some of the numbers match the waterfall, the total do not and brand trends do not for CKOREO | 1
2025-02-20 12:00 | Sonny | Super | Opened | High | P2-TS-D-05 | Calculation Error | Unable to input digits | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | I am trying to Enrich Ship to Cx Ratio in the Override Ship to Cx Ratio Key Figure. | I couldn't input digits | 2
2025-02-20 12:00 | Charles | Super | In Progress | High | P2-TS-D-03 | Calculation Error | CY Total CX mismatch | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CY Total CX calculation is not matching up with Nielsen actuals | Though calculation is correct for forecast (PY + all MBDs), I would expect the CY Total CX to be pulled in straight from Nielsen actuals | 2
2025-02-19 12:00 | Theodore | Normal | Opened | Medium | P2-TC-F-02 | Calculation Error | Duplicate data entries in tables | Set up the Shipment view for one or more IBP Subfamilies | Pulled up CRRICETHINS and CRSMALLWT for shipment views | Seeing double entries/rows for CRRICETHINS in the data tables. | 2
2025-02-19 12:00 | Amber | Super | Opened | Medium | P2-TC-F-03 | Mapping Alignment | Missing data in table | Set up the Shipment view for IBP Category, Brand, and IBP Subfamily | Missing Data when I choose MUPs, Oreo and GR Variety Pack in the Total Cx to Tracked Shipment table | I expected to see data in the last two rows | 2
2025-02-19 12:00 | Matheus | Normal | Opened | Medium | P2-TC-F-02 | Calculation Error | Incorrect key figure aggregation | Set up the Shipment view for one or more IBP Subfamilies | Selection: CLUBMUPS & GRVARIETYPACK | I would like to have one key figure for the total of the sub fam and for that not to depend on the number of brands in the sub fam. If that is not the case then I should be seeing many more key figure lines since there are more than just 2 brands in the IBP subfam. | 2
2025-02-19 12:00 | David | Super | Opened | Critical | P2-TC-F-02 | Calculation Error | Duplicate rows with different numbers | Set up the Shipment view for one or more IBP Subfamilies | CX Oreo is giving twice as many rows as CKOREOFS - it seems to be a duplication error on CKOREO but the numbers are very different | I was expecting to see the same number of rows for both Subfamilies and it was odd that CKOREO had repeats with different numbers | 2
2025-03-13 12:00 | Rachel | Super | Opened | High | P3-EE-R-01 | Format Modification | Export data size error | Export data in an Excel file for a preset IBP Category, Brand, DP Owner, and SF. | I cannot export the Total Biscuit becase there is an error: 'export data is too large' | filter used: Super category Biscuit Ex Bars, IBP Category All, IBP Brand All, Demand Planner Owner All, IBP Sufmaily All | 3
2025-03-17 12:00 | Manoel | Super | Opened | Critical | P3-EE-D-07 | Calculation Error | Incorrect YoY PPA Base Lbs/TDP | Check the Actual+Forecast values in order of magnitude for all the drivers. | "YoY PPA Base Lbs/TDP (Month)" Values are showing up incorrecting in the Core Base Velocity section of SWA but the export is correct | See "Core Base Velocity" tab | 3
2025-03-14 12:00 | Manoel | Super | Opened | Low | P3-EE-D-09 | Visualization Issue | Error in Absoluter Volume Section | Validate if user is able to drill down to Brand level/Category/Sub Family level and visualize all drivers volumes for actual & forecast window. Note: Actual window leverages Nielsen Cx actual ratio while forecast uses Cx% provided as manual input for SF-Brand Disagg. | Summary - Visuals "Absoluter Volume" section is showing and error message | Tried this for IBP Brand = Triscuit; also tried for individual IBPSFs and got the same error | 3
2025-03-14 12:00 | Manoel | Super | Opened | Medium | P3-EE-D-10 | Calculation Error | Incorrect Disaggregation Percentages | Validate the calculation of Category-Brand level forecast to ensure SF-Brand Disagg is carried out appropriately. | CX% Disagg does not appear to be using the right allocation (percentages based on the input files) | See "CX to Shipment" tab of GRVALUE SAVORY 6CT columns U-AD | 3
2025-03-14 12:00 | Manoel | Super | Opened | Low | P3-EE-D-11 | Calculation Error | Incorrect percentage allocation used | Validate the calculation of Category-Brand level total ship adjustments to ensure SF-Brand Disagg is carried out appropriately. | Inventory % Disagg does not appear to be using the right allocation (percentages based on the input files) | See "Tracked Shipment" tab of the GRVALUE SAVORY 6CT | 3
2025-03-13 12:00 | Matheus | Normal | Opened | Critical | P3-EE-R-01 | Format Modification | Error during Excel export | Export data in an Excel file for a preset IBP Category, Brand, DP Owner, and SF. | I get an error message | I should be able to export the data. | 3
2025-02-14 12:00 | Sonny | Super | Closed | Medium | P1-TC-D-11 | Calculation Error | Small variance in Cx$ value | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CKOREO tested. Aiming to match Cx$ value between SWA and NID Data | Data has small variance between the two | 1
2025-02-17 12:00 | Sonny | Super | Closed | Medium | P1-TC-D-13 | Calculation Error | TDP Actuals Discrepancy | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Tested CKOREO. Used SWA UAT NIQ Reports to look for TDP actuals and compared to TDP Actuals from SWA | Data sources are not matching | 1
2025-02-13 15:00 | Theodore | Normal | Closed | High | P1-TC-D-10 | Calculation Error | Enrichment impact on forecasts | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | Updating brand baseline through enrichments | Expecting brand baseline to increase base on enrichments input, but data is still appearing as 0 in table | 1
2025-02-14 12:00 | Amber | Super | Closed | Low | P1-TC-F-04 | Mapping Alignment | "All" selection functionality issue | Set up the Consumption view for IBP Category, Brand, DP Owner, and IBP Subfamily | I selected a DP Owner and "All" in the IBPSF Selector - no data was returned | I expected I'd see the whole desk when I select "All" - if all doesn't work, should it be an option? | 1
2025-02-14 12:00 | Amber | Super | Closed | Low | P1-TC-F-07 | Mapping Alignment | Misaligned month and data | The tables are clear and easy to navigate | Jan '24 has no data underneath it - I think the names of the months are not aligned with data below it. | I expected monthly titles and data below it to align; also for navigation, we should "freeze panes" for the top so you can see the selection you made regardless of where you are on the screen | 1
2025-02-14 12:00 | Manoel | Super | Closed | Medium | P1-TC-D-24 | Mapping Alignment | Incorrect Consumption LBS Mapping | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Consumption LBS coming from NIM should be considered Base LBS and Total Lbs but they are getting populated as Total LBS - Can we keep the logic as-is and pull in the same forecast for Base LBS as Total LBS? TDP and Total LBS are coming in correctly for all innovation tested (CLIF BAR 6 PACK and CKOREOTHINS) | See "Innovation IBP Sub Family" tab | 1
2025-02-14 12:00 | Manoel | Super | Closed | High | P1-TC-D-27 | Calculation Error | Base LBS/TDP missing calculation | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Base LBS/TDP is missing for the forecast horizon - should be a calculation of Base LBS / TDP. Other rows look good. $ is missing which is expected. | See "total IBP Sub Family" tab | 1
2025-02-14 12:00 | Manoel | Super | Closed | High | P1-TC-D-32 | Calculation Error | Incorrect total calculation representation | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Pass for CY Tracked Shipemt LBS and Gregorian Adj but fail for "CY Tracked Shipment Lbs (Total)". What is this row supposed to represent? It's only populated for Feb-25 to Dec-25 for CKBELVITA | "CX to Shipment" tab | 1
2025-02-12 14:23 | Manoel | Super | Closed | Medium | P1-TC-F-02 | Mapping Alignment | Incorrect search function behavior | Set up the Consumption view for one or more IBP Subfamilies | Searched for "CKNILLA", "CKNILLAFS", "CLUBMUPS" and only CKNILLA returned' Searched "GRGRAHAMS" and "CRGRAHAMSPARTY" and only "GRGRAHAMS" returned | Expected to see "CKNILLA" values and "CKNILLAFS" values | 1
2025-02-12 14:23 | Manoel | Super | Closed | Medium | P1-TC-F-03 | Mapping Alignment | Incorrect search results returned | Set up the Consumption view for IBP Category, Brand, and IBP Subfamily | Searched for "CKNILLA", "CKNILLAFS", "CLUBMUPS" and only CKNILLA returned' Searched "GRGRAHAMS" and "CRGRAHAMSPARTY" and only "GRGRAHAMS" returned | Same issue as P1-TC-F-02: "When selecting more than one IBP Subfamily, they will not be aggregated, and an extra column with the IBP SF will appear" does not happen | 1
2025-02-13 15:00 | Jose | Normal | Closed | Low | P1-TC-R-03 | Mapping Alignment | Missing MUPS Filter Option | Adjust Summary IBP Category Breakdown to your brand and evaluate the data quality for the MUPS line only. | not an option to adjust to MUPS only , the information does not change | the only filter available is IBP Brand | 1
2025-02-13 15:00 | Jose | Normal | Closed | Low | P1-TC-R-04 | Mapping Alignment | Channels Filter Missing Option | Adjust Summary IBP Category Breakdown to your brand and evaluate the data quality for the Channels line only. | not an option to adjust to Channels only , the information does not change | the only filter available is IBP Brand | 1
2025-02-13 15:00 | Jose | Normal | Closed | Low | P1-TC-R-05 | Format Modification | Inadequate filter options available | Adjust Summary IBP Category Breakdown to your brand and evaluate the data quality for the Food Service line only. | not an option to adjust to FoodService only , the information does not change | the only filter available is IBP Brand | 1
2025-02-13 15:00 | Matheus | Normal | Closed | Medium | P1-TC-D-01 | Mapping Alignment | Incorrect sub family mapping | Validate the volume/TDP is reflected in the right time frame for innovation product for respective sub families for a preset IBP Category, Brand, DP Owner, and SF. | The Innovations table doesn't work if I click total skus. it only shows data in the by sku view. I used GR20COUNTVP ibp subfam to check. Update: I discovered its because I didn’t have a brand selected. Again, this will not work for MUPs. We don’t care about the brand we need to see the ibpsub family in total. | to see a total of the innovations | 1
2025-02-14 12:00 | Matheus | Normal | Closed | Medium | P1-TC-D-05 | Mapping Alignment | Missing data in key figures | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp. There are a lot of key figures missing data | I expect to see a full table of data. | 1
2025-02-14 12:00 | Matheus | Normal | Closed | Medium | P1-TC-D-06 | Calculation Error | Missing key figures data | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp. There are key figures missing data | I expect to see a full table of data. | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-D-10 | Calculation Error | Total not matching SKUs | Validate the volume/TDP is reflected in the right time frame for innovation product for respective sub families for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp | I expect the total to reflect the sum of the skus | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-D-12 | Calculation Error | Negative values in forecast | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp | I should see values equal or greater than 0 | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-D-13 | Calculation Error | Negative Forecast Issue | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp | I assume a positive forecast lbs and tdps | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-D-14 | Calculation Error | Missing forecast data for 2026 | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, VP cookies, Moser GR, Gr20countvp | there should be 2026 data | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-D-15 | Calculation Error | Forecast calculations not working | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, Oreo, Moser GR, clubmups | calculations should work | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-D-17 | Calculation Error | Missing forecast data entries | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, Oreo, Moser GR, clubmups | should have data | 1
2025-02-14 12:00 | David | Super | Closed | Medium | P1-TC-D-05 | Calculation Error | Incremental lbs calculation discrepancy | Validation of calculation of Incremental related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Numbers should match the Input file for all attributes coming from Input Data, all other calculations to be validated by hand/system/excel | I pulled CKOREOFS from SWA UAT NIQ REPORTS and the incremental lbs for CKOREOFS were off in some months | 1
2025-02-14 12:00 | David | Super | Closed | High | P1-TC-D-07 | Calculation Error | Data mismatch with NIM file | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Numbers match an Excel validator/calculation by hand/system check. | There is one sku that launched Jan 2024 for CKOREOFS and the numbers do not tie to the NIM file | 1
2025-02-14 12:00 | David | Super | Closed | High | P1-TC-D-10 | Calculation Error | Mismatched totals in categories | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Numbers match an Excel validator/calculation by hand/system check. | I pulled CKOREOFS from SWA UAT NIQ REPORTS and the total Cx is off in multiple categories | 1
2025-02-14 12:00 | David | Super | Closed | High | P1-TC-D-22 | Calculation Error | Incorrect incremental lbs calculation | Validation of calculation of Incremental related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Numbers should match the Input file for all attributes coming from Input Data, all other calculations to be validated by hand/system/excel | OREOPartypack matched up in incremental forecast BUT incremental lbs in P12 were very negative in absolutes which isn't possible | 1
2025-02-14 12:00 | David | Super | Closed | High | P1-TC-D-24 | Calculation Error | Forecast fields not appearing | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Numbers match an Excel validator/calculation by hand/system check. | Lbs and TDPs are pulling in properly, but none of the other fields are coming in for forecast on Innovation on CKOREOFS. Jan 25 Data also appears incorrect? | 1
2025-02-14 12:00 | David | Super | Closed | Medium | P1-TC-D-25 | Mapping Alignment | Missing fields in forecast | Validate the volume/TDP is reflected in the right time frame for innovation product for respective sub families for a preset IBP Category, Brand, DP Owner, and SF. | Numbers should be visible for innovation product for 12 months starting with launch month and for next 12 months. | Lbs and TDPs are pulling in properly, but none of the other fields are coming in for forecast on Innovation on CKOREOThins. Data is in the correct months | 1
2025-02-12 14:23 | Jonathan | Normal | Closed | Low | P1-TC-D-01 | Mapping Alignment | SKU filtering issue | Innovation Cx | When filtered to 2 subfamilies (Clif 6 packs & Clif Singles), only the skus for 1 are populating (Clif Singles). When navigating the different skus the facts seem to be getting messed up. | To be able to see skus for both subfamilies. | 1
2025-02-17 12:00 | Jonathan | Normal | Closed | High | P1-TC-D-23 | Calculation Error | Understated volume for Clif Bar | Validate if the brand-category level volume matches the expected values or not for both Actuals and forecast window. | Both $ and lbs are understated for Clif Bar. | Retest: CX $ and Lbs actuals are still lower than what's in the NIQ input file. | 1
2025-02-12 14:23 | Sonny | Super | Closed | High | P1-TC-D-06 | Calculation Error | Incorrect Calculation Description | Validation of calculation of PPA related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Firstly, shouldn't the description say Validation of Calculation of "Category Trend?" | Seeing this test script issue from Row 4 to Row 8 | 1
2025-02-14 12:00 | Sonny | Super | Closed | High | P1-TC-D-09 | Mapping Alignment | Incorrect data time alignment | Validate the volume/TDP is reflected in the right time frame for innovation product for respective sub families for a preset IBP Category, Brand, DP Owner, and SF. | I am testing CRSMALLWT and crritzreg looking that lbs/TDP has an actuals in 2025 as it has launch in 2024. | No data found | 1
2025-02-14 12:00 | Sonny | Super | Closed | High | P1-TC-D-10 | Calculation Error | Discrepancy in data calculations | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CKOREO tested. Aiming to match base lbs value in SWA and NIQ Data | Data has small variance | 1
2025-02-14 12:00 | Sonny | Super | Closed | High | P1-TC-D-18 | Calculation Error | Recalculation not reflecting enrichment | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | Tested CKOREO. I added numbers in the enrichment KF, hit CTRL+ENTER. The data got reflected. When I hit recalculate the enrichment was gone and Total Brand Baseline remained the same prior to enriching it | Expected that Total Brand Baseline will recalculate to reflect enrichment | 1
2025-02-14 12:00 | Sonny | Super | Closed | High | P1-TC-D-41 | Mapping Alignment | Data sources mismatch | Validate if waterfall represent the volume correctly or not. | CKOREO tested. Trying to match the abs volume vs the yoy consumption waterfall | Data sources are not matching | 1
2025-02-13 15:00 | Theodore | Normal | Closed | Medium | P1-TC-D-06 | Mapping Alignment | Missing actuals data for Core | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Validating Core TDP data for CRSMALLWT | No actuals data appearing for Core TDP | 1
2025-02-13 15:00 | Theodore | Normal | Closed | High | P1-TC-D-08 | Calculation Error | Discrepancy in monthly data 2024 | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Validating untracked shipment data vs input file | Monthly data does not match for CKOREO 2024 FY | 1
2025-02-13 15:00 | Theodore | Normal | Closed | Medium | P1-TC-D-09 | Visualization Issue | Visualization Issue | Check the Actual charts for each of the previous test cases. | Viewing chart version of Core TDP data for CKOREO | Core TDP data in table is 0 but chart shows different numbers | 1
2025-02-12 14:23 | Theodore | Normal | Closed | Medium | P1-TC-F-08 | Visualization Issue | Missing line in chart | The graphs provided are easy to read | CY Incr Lbs line data is missing when viewing in Chart mode for a specific IBP subfamily | Expected to see two lines, one for PY Incr Lbs and another for CY Incr Lbs, but I'm only seeing PY Incr Lbs | 1
2025-02-13 15:00 | Theodore | Normal | Closed | Medium | P1-TC-R-04 | Mapping Alignment | Channels data not appearing | Adjust Summary IBP Category Breakdown to Channels data only and verify data quality. | Validating Channels data for Wheat Thins | No data appearing | 1
2025-02-13 15:00 | Theodore | Normal | Closed | Low | P1-TC-R-08 | Format Modification | Export format options missing | Export the data (filtered or not) into different formats. | Trying to export as CSV or PDF | Cannot see option to export CSV or PDF. Export button automatically exports data in xlsx. | 1
2025-02-13 15:00 | Theodore | Normal | Closed | Medium | P1-TC-R-09 | Visualization Issue | Waterfall Month Filtering Problem | Create a waterfall chart with the full dataset or part of it. | Trying to get a waterfall chart for a specific month | No data appearing when month is filtered. | 1
2025-02-13 15:00 | Theodore | Normal | Closed | Medium | P1-TC-R-10 | Visualization Issue | Waterfall Month Filtering Problem | Create a waterfall chart with the full dataset or part of it. | Trying to get a waterfall chart for a specific month | No data appearing when month is filtered. | 1
2025-02-13 15:00 | Theodore | Normal | Closed | Medium | P1-TC-R-11 | Visualization Issue | Visualization Issue | Create a waterfall chart with the full dataset or part of it. | Trying to get a waterfall chart for a specific month | No data appearing when month is filtered. | 1
2025-02-12 14:23 | Kelly | Super | Closed | High | P1-TC-D-03 | Calculation Error | Incorrect Pricing Elasticity Calculation | Validation of calculation of Pricing Action related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Pricing Elasticity per Pricing SKU- thinking this field should show -1 and it shows 0 | Looking at CKOREOFS | 1
2025-02-12 14:23 | Kelly | Super | Closed | Medium | P1-TC-D-04 | Calculation Error | TDP % calculation validation | Validation of calculation of TDP related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | TDP % changes look a little odd (picture in log). Maybe because there is no PY data? | Looking at CKOREOFS | 1
2025-02-14 12:00 | Kelly | Super | Closed | Medium | P1-TC-D-09 | Mapping Alignment | Actuals mismatch with CKOREOFS | Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | CKOREOFS/FSINANDOUT don’t match to my Cx lb actuals | CKOREOFS AND CKOREOFSINANDOUT | 1
2025-02-14 12:00 | Kelly | Super | Closed | High | P1-TC-D-26 | Calculation Error | Incorrect forecast calculation results | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Very High. Doesn’t look right | CKOREOFS | 1
2025-02-12 14:23 | Kelly | Super | Closed | Medium | P1-TC-F-08 | Visualization Issue | Missing Graphs for Section | The graphs provided are easy to read | I don’t have graphs for "Total Incremental CX Lbs" section | Error message: An error has occurred. Check your logs or contact the app author for clarification | 1
2025-02-14 12:00 | Amber | Super | Closed | High | P1-TC-D-02 | Calculation Error | Incorrect percentage calculation PPA | Validation of calculation of PPA related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | I checked GRGRAHAMs - one SKU is on the PPA sheet (#4717). I have a different % of IBPSF for this SKU - I calc 3.97% and SWA has 12.3%. Thus my Lbs impact is much lower than SWA's. | I expected the impact from PPA to be -196 and SWA has -606. | 1
2025-02-14 12:00 | Amber | Super | Closed | High | P1-TC-D-03 | Calculation Error | Pricing increase mismatch calculation | Validation of calculation of Pricing Action related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | USCANDYALLOTHER - the % Price Increase does not match the input file | According to the Pricing Input file, the price increase on the SKUs are 11.4%, 11,5% or 12.6%. SWA says 100% of SKUs are pricing and the increase is 10.13% which is lower than any of the price increases. I expected it to be blend of the three price increases. | 1
2025-02-14 12:00 | Manoel | Super | Closed | High | P1-TC-D-13 | Mapping Alignment | Missing UPC in forecast | Core TDPs Calculate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Had this as pass on 2/12 but discovered a defect with CKOREOTHINS which is missing a UPC from the Total TDP Forecast (UPC 4400004257). This UPC is on the Manual Mapping file but is mapped correctly to the CKOREOTHINS IBP Subfamily. Would like to see TDP Change in absolute values | See "Core TDP" Tab | 1
2025-02-13 15:00 | Manoel | Super | Closed | High | P1-TC-D-19 | Calculation Error | Incorrect PPA percentage calculation | Validation of calculation of PPA related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | For GRVARIETYPACK, PPA % Price Change per PPA SKU should show up as 7.7% starting in Mar-25 for 12 months per the Input File, but SWA is showing 7.7% for the entire horizon (before Mar-25) for CHIPS AHOY/NILLA/OREO/RITZ and blanks for the other Brands except in the month of Jan '25. | See "Core Base Velocity" tab | 1
2025-02-14 12:00 | Manoel | Super | Closed | High | P1-TC-D-20 | Calculation Error | PPA calculation timeframe issue | Validation of calculation of PPA related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Another issue is happening for CLIF BAR 6 PACK which should have the months Nov-24 to Apr-25 populatedin the "PPA Multiplier per PPA SKU Adjustment" row based on input file data columns BB-BG | See "Core Base Velocity" tab | 1
2025-02-14 12:00 | Manoel | Super | Closed | High | P1-TC-D-21 | Calculation Error | Double counting in TDP calculation | Validation of calculation of TDP related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Fail in Feb-25 for CKOREOTHINS as the Innovation SKU TDPs are getting double counted in CORE and INNOVATION (4400007788) - CORE TDPs should not include the TDP forecast from the TDP input file until Mar-25; Pass for CKBELVITA, fail for GRVARIETYPACK, pass for CLIF BAR 6 PACK | See "Core TDP" Tab | 1
2025-02-14 12:00 | Manoel | Super | Closed | High | P1-TC-D-28 | Calculation Error | Missing forecast calculation issue | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Forecast is missing for CLIF BAR 6 PACK on the "CORE IBP Sub Family" tab but should just be a simple calcuation of the forecasted Base LBS divided by forecasted Core TDPs | See "Core IBP Sub Family" tab | 1
2025-02-14 12:00 | Manoel | Super | Closed | High | P1-TC-R-01 | Mapping Alignment | Forecast data missing in export | Export data in an Excel file for a preset IBP Category, Brand, DP Owner, and SF. | Data on the "Total Drivers" tab is missing for "PY Incr Lbs", "YoY Incr Lbs", "CY Incr Lbs" and "YoY Total LBS" in the forecast horizon (Feb '25 onward). See Clif 6 Pack. | See "Total Drivers" tab | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-D-16 | Mapping Alignment | Missing core and innovation data | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Selections: MUPS, Oreo, Moser GR, clubmups | should have core and innovation data | 1
2025-02-14 12:00 | Matheus | Normal | Closed | High | P1-TC-R-03 | Mapping Alignment | Data missing for MUPS line | Adjust Summary IBP Category Breakdown to your brand and evaluate the data quality for the MUPS line only. | I selected MUPs and there wasn’t any data. | should have data | 1
2025-02-14 12:00 | David | Super | Closed | Critical | P1-TC-D-28 | Calculation Error | CKOREOFS CORE discrepancy without innovation | Calculate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Numbers match an Excel validator/calculation by hand/system check. | CKOREOFS CORE does not equal TOTAL when there is no innovation in those months | 1
2025-02-20 12:00 | Sonny | Super | Closed | Critical | P2-TS-D-04 | Calculation Error | Discrepancy in ratio calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | I am trying to calculate Cx to Ratio Calculation for actuals. I'm dividing actuals shipment from SWA by Actual Total Lbs Cx and comparing it to the Ship to Cx Ration in SWA | I'm expecting that manually Dividing Shipment by Cx will result to a number equal to the Ship to Cx Ratio in SWA. Logic check and SWA data didn't match | 2
2025-02-20 12:00 | Sonny | Super | Closed | Critical | P2-TS-D-08 | Calculation Error | Incorrect Gregorian adjustment calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Testing CKOreo for Gregorian Adjustment (Days) for actuals. | I was expecting that the result of my Logic Check will match the Gregorian adjustment Key Figure I'm seeing in SWA. The numbers didn't match | 2
2025-02-20 12:00 | Sonny | Super | Closed | Medium | P2-TS-D-16 | Calculation Error | Forecast Cx Ratio Mismatch | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | I am trying to calculate Cx to Ratio Calculation for forecast. | I'm expecting that manually Dividing Shipment by Cx will result to a number equal to the Ship to Cx Ratio in SWA. Logic check and SWA data didn't match | 2
2025-02-21 12:00 | Sonny | Super | Closed | High | P2-TS-D-30 | Calculation Error | Mismatched Total Shipment Calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Testing CKOreo for Total Shipment Actuals | I was expecting that SWA's Total Shipment Lbs will match the Logic Check | 2
2025-02-19 12:00 | Theodore | Normal | Closed | Medium | P2-TC-F-03 | Mapping Alignment | Duplicate entries in data tables | Set up the Shipment view for IBP Category, Brand, and IBP Subfamily | Pulled up CRRICETHINS and CRSMALLWT for shipment views | Seeing double entries/rows for CRRICETHINS in the data tables. | 2
2025-02-19 12:00 | Theodore | Normal | Closed | Medium | P2-TC-F-04 | Mapping Alignment | Duplicate data entries issue | Set up the Shipment view for IBP Category, Brand, DP Owner, and IBP Subfamily | Pulled up CRRICETHINS and CRSMALLWT for shipment views | Seeing double entries/rows for CRRICETHINS in the data tables. | 2
2025-02-21 12:00 | Theodore | Normal | Closed | Medium | P2-TS-D-06 | Mapping Alignment | Data mismatch on table | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Validating returns and liquidations actuals on CRSMALLWT | Data on Returns and Liquidations table do not match input files. | 2
2025-02-20 12:00 | Amber | Super | Closed | Medium | P2-TC-F-06 | Mapping Alignment | Slicers setup challenge | It is easy to set up the slicers to get the data I need | The slicers are not easy - it's a challenge to pull a desk or anything higher | All does not work in IBPSF - so pulling a desk is tedious | 2
2025-02-20 12:00 | Amber | Super | Closed | High | P2-TS-D-09 | Calculation Error | Discrepancy in Data Validation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Jan '24: Halls Large Bags; SWA: 2,984,304: 3,535,916 | Go to Tracked Shipment tab | 2
2025-02-20 12:00 | Amber | Super | Closed | Medium | P2-TS-D-11 | Mapping Alignment | Missing data for selection | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | No Untracked data for Halls in 2024 | I selected Halls Large Bags Untracked was missing | 2
2025-02-20 12:00 | Amber | Super | Closed | Medium | P2-TS-D-12 | Visualization Issue | Chart data line ordering | Check the Actual charts for each of the previous test cases. | In Cx to Tracked Shipment Chart, the "CY Total Lbs" line is on the bottom. I expected that to be top line - it's Total, shouldn't it be? | CRGRAHAMS | 2
2025-02-20 12:00 | Amber | Super | Closed | Critical | P2-TS-D-15 | Calculation Error | Incorrect PY Total Lbs | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | March '25: Halls Large Bags: SWA 1,989,719, Amy: 1,227,286 | Go to Total Drivers Tab, PY Total Lbs is not right | 2
2025-02-20 12:00 | Amber | Super | Closed | Critical | P2-TS-D-16 | Calculation Error | Incorrect forecast ratio values | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Mar '25 Halls Large Bags Ratio: SWA 1.360, Amy 1.667 | Go to Tracked Shipment tab | 2
2025-02-20 12:00 | Amber | Super | Closed | High | P2-TS-D-17 | Calculation Error | Incorrect ratio calculations in export | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | I put in new Ratios for Mar-Jun '25 for Halls Small Bags | I expected to see the new ratios in my export (they weren't there) and I expected the calcs to be correct (they weren't). They were off similar amounts (not 100% exact) to the defect in the Build/Burn script (P2-TS-D-18). See Tracked Shipment tab. | 2
2025-02-20 12:00 | Amber | Super | Closed | High | P2-TS-D-18 | Calculation Error | Incorrect forecasted build/burn calculation | Validation of calculation of Forecasted Build/Burn related drivers for forecast timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Feb '25 Halls Small Bags, SWA: -498,669, Amy: -498,458 | See Tracked Shipment tab | 2
2025-02-20 12:00 | Amber | Super | Closed | Critical | P2-TS-D-19 | Calculation Error | Missing data in forecast | Validation of calculation of Liquidations and Returns for forecast timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Returns and Liquidations missing a month - Feb '25 is not listed for Halls Small Bags; Also, couldn't check Lbs since the input files were in $$s - I didn't see an input file with GR/Lb conversion rates | I expected to see the month even if the #s are zero | 2
2025-02-20 12:00 | Amber | Super | Closed | High | P2-TS-D-21 | Calculation Error | Forecast validation discrepancy | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Mar '25: Halls Large Bags; SWA: 2,706,502, Amy: 1,614,786 | Go to Tracked Shipment tab | 2
2025-02-19 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-04 | Calculation Error | Incorrect ratio calculation displayed | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Jan-24 ratio should be "CY Total Tracked Shipments" / "CY total CX Lbs" but that is not the value that is shown (Can only easily validate Jan-25 using Jan-24) | CRGRAHAMS Tab "Tracked Shipments" | 2
2025-02-21 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-10 | Calculation Error | Inconsistent Tracked Shipment Calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Checking "CY Tracked Shipment Lbs (Total)" on the CX to Shipment tab and it is different from the "CY Total Tracked Shipment" line on the Tracked Shipment tab. I would expect these to be the same | CRPREMIUM "CX to shipment" and "Tracked Shipment" tabs | 2
2025-02-21 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-22 | Calculation Error | Tracked Shipment Value Mismatch | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Testing the "CY Tracked Shipment Lbs (Total) on the CX to Shipment table. Would expect values to equal "CY Total Tracked Shipment" on the Tracked Shipment tab. | CRPREMIUM "CX to shipment" and "Tracked Shipment" tabs | 2
2025-02-21 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-30 | Calculation Error | Incorrect data version inclusion | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | SAC data is getting doubled as it is including both "Actual" and "CF" versions but should only add up rows that are "Actual" | CRPREMIUM "Total Shipment $ + Lbs" tab | 2
2025-02-24 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-33 | Calculation Error | Incorrect Year-over-Year Value | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Returns is showing a YoY value for Feb -25 but should be flat YoY for all forecasted months - thinking this may have to do with Feb -25 missing from the returns table | CRPREMIUM "Total Shipment Drivers" Tab | 2
2025-02-19 12:00 | Matheus | Normal | Closed | Medium | P2-TS-D-05 | Format Modification | Labeling confusion and adjustment | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Selection: Mups, CA!, MoserGR & GRTraypack | I would think this should be the total of tracked and untracked shipment lbs. | 2
2025-02-19 12:00 | Matheus | Normal | Closed | High | P2-TS-D-06 | Calculation Error | Inconsistent shipment data across tables | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | I have different values for CY tracked shipment lbs key figure in different tables. | the values should be the same for every table | 2
2025-02-19 12:00 | David | Super | Closed | High | P2-TS-D-03 | Calculation Error | Inaccurate monthly actuals calculation | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Cx Lb actuals look to be messed up (CKOREOFS) - Some months are close, others are not. | Feb is very close, but March is off by over 10% (2.7MM lbs) | 2
2025-02-19 12:00 | David | Super | Closed | Medium | P2-TS-D-05 | Calculation Error | Missing calculations button for forecast | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | Numbers would not stick in Actuals + Forecast (No Calculation button). It passed in the Forecast tab | I tried to enter new numbers into the enrichment cells, but there is no calculations button | 2
2025-02-19 12:00 | Theodore | Normal | Closed | High | P2-TC-F-07 | Calculation Error | Inconsistent data representation issue | The tables are clear and easy to navigate | Pulled up CRSMALLWT and viewing data for Total Shipment Drivers - GR$ | PY Total GR$ data is in millions and not consistent with the data in the rest of the table. | 2
2025-02-19 12:00 | Theodore | Normal | Closed | Medium | P2-TC-F-08 | Visualization Issue | Graph component removal option | The graphs provided are easy to read | Pulled up CRSMALLWT and viewing charts | Graphs in components view have too many lines. Can we add option to remove certain components from the views? | 2
2025-02-19 12:00 | Amber | Super | Closed | High | P2-TS-D-04 | Calculation Error | Validation of actuals required | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | Jan '25 Halls Large Bags Ratio: SWA 2.043, Amy 2.787 | Go to Tracked Shipment tab | 2
2025-02-20 12:00 | Amber | Super | Closed | High | P2-TS-D-06 | Calculation Error | Incorrect calculation for Actual Build/Burn | Validation of calculation of Actual Build/Burn related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Jan '25 Halls Large Bags Build/Burn: SWA 1,540,415, Amy 708,655 | Go to Tracked Shipment tab | 2
2025-02-20 12:00 | Amber | Super | Closed | Critical | P2-TS-D-07 | Calculation Error | Incorrect liquidation and returns calculation | Validation of calculation of Liquidations and Returns for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Oct '24: Halls Large Bags Liquidation: SWA 12,371, Amy 12,286 | Go to Amy - Liq tab | 2
2025-02-19 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-06 | Calculation Error | Build/Burn Calculation Validation | Validation of calculation of Actual Build/Burn related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Actualized Build/Burn should equal Shipment Volume (lbs) - Untracked Shipment - Liquidation - CY Total CX Lbs - Gregorian Adjustment + Returns | CRGRAHAMS Tab "Tracked Shipments" | 2
2025-02-19 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-19 | Calculation Error | Missing February 2025 in table | Validation of calculation of Liquidations and Returns for forecast timeframe for a preset IBP Category, Brand, DP Owner, and SF. | Table is missing Feb 2025! | CRPREMIUM | 2
2025-02-24 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-31 | Calculation Error | Incorrect year data displayed | Validate Actuals for a preset IBP Category, Brand, DP Owner, and SF. | "PY Total Tracked Shipments" on the Total Shipment Drivers table is showing Current Year Total Tracked Shipments | CRPREMIUM "Total Shipment Drivers" Tab | 2
2025-02-24 12:00 | Manoel | Super | Closed | Critical | P2-TS-D-32 | Calculation Error | Forecast shipment volume discrepancy | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Shipment Volume (lbs) for the forecast should equal CY Total Tracked Shipments + Untracked + Liquidations, although liquidations will be zero | see row 34 on "Tracked Shipment" tab | 2
2025-02-19 12:00 | Matheus | Normal | Closed | High | P2-TS-D-04 | Format Modification | Unable to edit field | Validate if enrichment put by user is impacting the overall total forecast and related attributes for a preset IBP Category, Brand, DP Owner, and SF. | Selection: Mups, CA!, MoserGR & GRTraypack. I cant edit the override ship to cx ratio. I've double clicked in multiple spots and nothing happens. | I should be able to edit the field. | 2
2025-02-19 12:00 | David | Super | Closed | Critical | P2-TS-D-06 | Calculation Error | Unreasonable build calculation discrepancy | Validation of calculation of Actual Build/Burn related drivers for actual timeframe for a preset IBP Category, Brand, DP Owner, and SF. | The supposed build in the past is totally unreasonable - suggesting we built over 20MM lbs per month every month in 2024 | I can't even get the calculations to match the ship to cx ratios | 2
2025-02-19 12:00 | David | Super | Closed | Medium | P2-TS-D-13 | Visualization Issue | Bar chart missing numbers | Validate Forecast for a preset IBP Category, Brand, DP Owner, and SF. | Total Cx to Tracked Shipment chart isn't adding value | Bar chart with no numbers on the axis | 2
2025-03-13 12:00 | Sonny | Super | Closed | Medium | P3-EE-D-01 | Mapping Alignment | Data export mismatch with table | Check the Actual values in order of magnitude for all the drivers. | I am trying to validate below result for Oreo Channels: Numbers are within the expected bounds/order of magnitude for all drivers, in tune with the previous two phases. | The Oreo Brand Channel Core Base lbs/TDP Actuals data export is not tallying up to any paramaters shown in the SWA table | 3
2025-03-13 12:00 | Sonny | Super | Closed | Medium | P3-EE-F-05 | Calculation Error | Table refresh after reset | Remove any slicing of data that has been set up. | I am trying to validate below result: After Clicking the [Reset filters] button, the slicers for IBP Category, IBP Brand, and DP Owner should have "All" as values, and the slicer for IBP SF should be empty. Tables should display "No data available in table". | After hitting "Reset Filters" the Super Category, IBP Category, IBP Brand and Demand Planner Owner reflected "All" and the IBP Sub Family was empty. However, the table did not refresh. I have to click "Run Query" first, before the table displayed "No data available in table" | 3
2025-03-13 12:00 | Sonny | Super | Closed | Critical | P3-EE-F-02 | Mapping Alignment | Incomplete data mapping duplication | Set up the Consumption & Shipment view for one or more IBP Subfamilies | Exporting CRRICETHINS and CRSMALLWT data | Export shows duplicating key figures with incompletely mapped data. Numbers also do not match SWA. | 3
2025-03-13 12:00 | Sonny | Super | Closed | Critical | P3-EE-F-03 | Mapping Alignment | Incorrect key figure mapping | Set up the Consumption & Shipment view for IBP Category, Brand, and IBP Subfamily | Exporting CRRICETHINS and CRSMALLWT data | Export shows duplicating key figures with incompletely mapped data. Numbers also do not match SWA. | 3
2025-03-13 12:00 | Sonny | Super | Closed | High | P3-EE-R-01 | Mapping Alignment | Key figures duplication and mismatch | Export data in an Excel file for a preset IBP Category, Brand, DP Owner, and SF. | Exporting CRRICETHINS and CRSMALLWT data | Export shows duplicating key figures with incompletely mapped data. Numbers also do not match SWA. | 3
2025-03-13 12:00 | Rachel | Super | Closed | Low | P3-EE-D-07 | Visualization Issue | Drill down visual error | Validate if user is able to drill down to Brand level/Category/Sub Family level and visualize all drivers volumes for actual & forecast window. Note: Actual window leverages Nielsen Cx actual ratio while forecast uses Cx% provided as manual input for SF-Brand Disagg. | Error message for Summary / Visuals | An error has occurred. Check your logs or contact the app author for clarification | 3
2025-03-13 12:00 | Kelly | Super | Closed | High | P3-EE-D-07 | Calculation Error | Incorrect Forecast Values Display | Check the Actual+Forecast values in order of magnitude for all the drivers. | no $ forecast in CKOREOFSINANDOUT. Checked more than one sub family too. 2 photos. 2 different sections | https://teams.mdlz.com/sites/usibpteam/Shared%20Documents/General/Enterprise%20Business%20Planning%20Journey/04_MBDs/13_SWA_FIG/UAT/3%20-%20E2E%20Total%20View/Flanagan,%20Kelly%20R/6.png | 3
2025-03-13 12:00 | Manoel | Super | Closed | Critical | P3-EE-D-01 | Calculation Error | Actual values mismatch in magnitude | Check the Actual values in order of magnitude for all the drivers. | Actuals: CY Tracked Shipments does not appear to equal Total Shipments - Liquidations - Untracked | Testing for CLUBCR04782TRIS, see row 24 of "Total Shipment $ + Lbs" tab | 3
2025-03-13 12:00 | Manoel | Super | Closed | High | P3-EE-D-03-3 | Calculation Error | Forecast magnitude incorrect values | Check the Forecast values in order of magnitude for all the drivers. | Tried to add 20K to brand baseline for an IBP Subfamily that had 0 lbs/TDP in the prior year and got an error; maybe this has not been fixed yet from previous UAT defects | Filters: IBP Sub Family = CLUBCR04782TRIS | 3
2025-03-14 12:00 | Manoel | Super | Closed | Critical | P3-EE-D-04 | Visualization Issue | Missing forecast in chart | Check the Forecast charts for all the drivers. | This is probably a repeated defect, but Total IBP Sub Family (NIQ Facts) table should show the CX LBS forecast for the entire horizon - it is missing for the forecast | GRVALUE SAVORY 6CT | 3
2025-03-13 12:00 | Manoel | Super | Closed | High | P3-EE-D-07-1 | Visualization Issue | Missing data in visualization | Check the Actual+Forecast values in order of magnitude for all the drivers. | Actuals & Forecast: Untracked values are not visible in SWA when there is no CX volume for that IBP Subfamily | Example is GRECOMM IBPSubfamily | 3
2025-03-14 12:00 | Manoel | Super | Closed | Low | P3-EE-D-07-3 | Calculation Error | Mismatched values across tables | Check the Actual+Forecast values in order of magnitude for all the drivers. | "CY Tracked Shipment Lbs" on the Gregorian Adjustment of Consumption table should be the same as "CY Tracked Shipment Lbs" on the Tracked Shipment Adjustments table | Tested for GRVALUE SAVORY 6CT | 3
2025-03-13 12:00 | Manoel | Super | Closed | Critical | P3-EE-R-01 | Format Modification | Export Functionality Error | Export data in an Excel file for a preset IBP Category, Brand, DP Owner, and SF. | Getting an error when trying to export - no option to export as Excel | Happening for NILLA, CRGRAHAMS, CLUBCR04782TRIS, and others | 3
2025-03-13 12:00 | Matheus | Normal | Closed | Critical | P3-EE-D-01 | Calculation Error | Missing value calculation discrepancy | Check the Actual values in order of magnitude for all the drivers. | I feel like there should be values in Yoy incr cx$/lb % | I feel like there should be values in Yoy incr cx$/lb % | 3
2025-03-13 12:00 | Matheus | Normal | Closed | Critical | P3-EE-D-03 | Calculation Error | Negative forecasted incremental values | Check the Forecast values in order of magnitude for all the drivers. | forecasted CY incremental lbs are negative | it can be 0 but it should not be negative | 3
2025-03-13 12:00 | Matheus | Normal | Closed | Critical | P3-EE-F-02 | Calculation Error | Data not displaying after query | Set up the Consumption & Shipment view for one or more IBP Subfamilies | No data populates unless I run the query | I expected to see data after selecting all the slicers. | 3
2025-03-13 12:00 | Matheus | Normal | Closed | High | P3-EE-F-05 | Visualization Issue | Data reset not working | Remove any slicing of data that has been set up. | There was still data in the tables/charts after hitting reset | I expected for the table and charts would show no data. | 3
2025-03-13 12:00 | David | Super | Closed | Critical | P3-EE-D-01 | Calculation Error | Output not matching input files | Check the Actual values in order of magnitude for all the drivers. | I am comparing the output for CKOREO FS to the input files that are feeding the calculation for Category Base Trends | I wasn't sure which key figure is being calculated so I tried PY Tracked shipment lbs, PY Cx lbs, and PY Gregorian cx lbs - all of them got me to an output that is similar to MBDS, but ultimately not matching | 3
2025-03-13 12:00 | David | Super | Closed | Critical | P3-EE-D-03 | Calculation Error | Discrepancy in calculated values | Check the Actual values in order of magnitude for all the drivers. | I am comparing the output for CKOREO FS to the input files that are feeding the calculation for Category Base Trends for Forecast | I wasn't sure which key figure is being calculated so I tried PY Tracked shipment lbs, PY Cx lbs, and PY Gregorian cx lbs - all of them got me to an output that is similar to MBDS, but ultimately not matching | 3
2025-03-13 12:00 | David | Super | Closed | High | P3-EE-D-05 | Calculation Error | Discrepancies in monthly totals | Validate if PPD is captured properly and removed from Total Forecast. | I am comparing the PPD output for CKOREOFS to the input file for PPDs | There were descrepancies in some of the months (Feb and May) - Feb is off by 700K lbs, May is off by 40K lbs Mar is off like 700 lbs - the rest are within 10 | 3
2025-03-13 12:00 | David | Super | Closed | Medium | P3-EE-D-07 | Calculation Error | Inconsistent driver tab calculations | Check the Actual+Forecast values in order of magnitude for all the drivers. | I am not able to tie the cat base trends In the driver tab to any calculation | In the tab Cat base Trends Ritzreg you can see the calculations I tried to get to the numbers in the drivers tab. Maybe I'm doing it wrong but I was not able to get the numbers to tie, thought they are directional | 3
2025-03-13 12:00 | David | Super | Closed | Critical | P3-EE-D-09 | Visualization Issue | Missing visual in volume tab | Validate if user is able to drill down to Brand level/Category/Sub Family level and visualize all drivers volumes for actual & forecast window. | There is no visual on the absolute volume tab due to an error | Error message: An error has occurred. Check your logs or contact the app author for clarification. See visualization tab on attached file for screenshot | 3
2025-03-13 12:00 | David | Super | Closed | High | P3-EE-D-10 | Calculation Error | Incorrect category-brand level forecast | Validate the calculation of Category-Brand level forecast to ensure SF-Brand Disagg is carried out appropriately. | I checked OREOs total Cx, Triscuit Total Cx, and Ritz Total Cx. Triscuit was perfect, but Oreo was off by ≈$40MM and 5MMlbs and Ritz was off ≈$50MM and 7MM lbs. | Ritz example is shown the total Cx actuals tab as an example | 3